## Sprint Backlog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| US 100 | 1 | Understanding Requirements , Desigining Class diagram and use case diagram , Unit test cases | Diksha | 21/09/2020 | 1 Day | 1 Day | Done
|  | 2 | Designing database diagram and unit test cases | Diksha | 22/09/2020 | 1 Day | 1 Day | Done
| US 101 | 1 | Understanding Requirements , Desigining Class diagram and use case diagram , Unit test cases | Kartik | 21/09/2020 | 1 Day | 1 Day | Done
|  | 2 | Designing database diagram and unit test cases | Kartik | 22/09/2020 | 1 Day | 1 Day | Done
| US 103 | 1 | Understanding Requirements , Desigining Class diagram and use case diagram , Unit test cases | Shubham | 21/09/2020 | 1 Day | 1 Day | Done
|  | 2 | Designing database diagram and unit test cases | Shubham | 22/09/2020 | 1 Day | 1 Day | Done
| US 104 | 1 | Understanding Requirements , Desigining Class diagram and use case diagram , Unit test cases | Srashti | 21/09/2020 | 1 Day | 1 Day | Done
|  | 2 | Designing database diagram and unit test cases | Srashti | 22/09/2020 | 1 Day | 1 Day | Done
| US 105 | 1 | Understanding Requirements , Desigining Class diagram and use case diagram | Prashant | 21/09/2020 | 1 Day | 1 Day | Done
|  | 2 | Designing database diagram and unit test cases | Prashant | 22/09/2020 | 1 Day | 1 Day | Done
List User Story steps that were not completed at Sprint End

## Product Backlog
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 |  | M | US 100
2
3
4
5
6
7
8 |  | M | US 101
9
10
11
12
13
14
15 |  | M | US 102
16
17
18
19
20 |  | M | US 103
21
22
23
24
25
26
27
28 |  | M | US 104
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46